NATIONAL INFORMATION ECOSYSTEM AND AI PROGRAMME

# Phase 1 Package Review and Phase 2 Design Brief

Review of Phases 1A to 1G  |  Version 1.0  |  September 2026

## Review conclusion

Phase 1 is substantively complete and forms a coherent operational system. It covers diagnosis, evidence collection, maturity interpretation, ecosystem mapping, use-case prioritization, controlled experimentation and national planning. It is suitable for a structured country field test. It should not yet be treated as a finished global standard or mass-delivery product: a limited harmonization and field-validation cycle is required before broad rollout.

## Decision

Proceed to Phase 2 curriculum design now, using the Phase 1 instruments as the practical backbone. In parallel, prepare a controlled Version 1.1 harmonization release after the first country application. Do not delay the curriculum until every instrument is cosmetically identical; correct the cross-instrument control issues identified in this review before the first formal field deployment.

| Review question | Conclusion |
| --- | --- |
| Is the coverage complete enough for field use? | Yes. All essential levels, data origins, quality dimensions, institutional conditions and pilot controls are represented. |
| Do the instruments form one workflow? | Yes, but handoffs require a common identifier and terminology crosswalk. |
| Are safeguards adequate? | Strong. Gate logic, professional authority, confidentiality, quality and fallback are consistently protected. |
| Can resource-constrained systems use it? | Yes, if a minimum viable pathway and facilitated support are provided. |
| What should happen next? | Begin Phase 2 design and prepare a field-test and harmonization pack. |

# 1 Scope and review method

The review examined each Phase 1 component as part of one decision chain. It considered scope, users, evidence standards, terminology, duplication, handoffs, safeguards, usability and suitability for centralized, decentralized, advanced and resource-constrained statistical systems.

| Component | Primary function | Review perspective |
| --- | --- | --- |
| 1A Diagnostic framework | Defines units, dimensions, maturity, evidence and gates. | Is the assessment architecture complete and defensible? |
| 1B Readiness questionnaire | Collects institutional and national-system evidence. | Can respondents supply evidence rather than opinion? |
| 1C Scoring workbook | Converts evidence into profiles, targets, gates and actions. | Does scoring preserve uncertainty and critical safeguards? |
| 1D Ecosystem mapping toolkit | Maps actors, assets, flows, needs, coordination and risks. | Does it represent the national information system beyond the NSO? |
| 1E Use-case toolkit | Registers, screens, gates and selects proposals. | Does value ranking remain subordinate to risk and authority? |
| 1F Pilot protocol | Tests selected uses against approved benchmarks. | Can a pilot produce a defensible statistical assurance decision? |
| 1G Synthesis and action-plan template | Converts evidence into a national programme. | Does it create an owned, costed and monitored roadmap? |

## Review criteria

Logical completeness from information need to monitored production.

Consistency of roles, risk concepts, evidence and gate decisions.

Traceability of findings and decisions across instruments.

Fitness for different statistical domains and data origins.

Proportionality to consequence and national resource constraints.

Ability to support practical learning and institutional change.

# 2 Architecture of the package

| Decision stage | Instrument | Authoritative output | Feeds |
| --- | --- | --- | --- |
| Define the assessment | 1A | Scope, dimensions, maturity rules and evidence standard. | 1B and 1C |
| Collect evidence | 1B | Responses, references, gaps and respondent confidence. | 1C and 1G |
| Interpret readiness | 1C | Dimension profile, target gaps, confidence, gate decision and actions. | 1E and 1G |
| Map the ecosystem | 1D | Stable IDs for institutions, assets, flows, users, coordination and risks. | 1E and 1G |
| Select opportunities | 1E | Prioritized portfolio, risk class, gates and decision log. | 1F and 1G |
| Test controlled pilots | 1F | Charter, benchmark, validation, incident evidence and assurance decision. | 1G and production governance |
| Approve national action | 1G | Operating model, sequenced actions, financing, indicators and annual review. | Phase 2 and implementation |

The architecture is strong because no instrument attempts to do everything. The central design choice—separate maturity profiles, evidence confidence and non-compensatory gates—protects the programme from superficial scoring and technology-led investment.

# 3 Major strengths

| Strength | Why it matters |
| --- | --- |
| National information ecosystem rather than NSO-only view | Captures sector producers, administrative sources, research information, geospatial data, private holders and users. |
| Four assessment levels | Distinguishes national-system, organization, workflow or use case, and individual capability. |
| No single readiness ranking | Prevents strong technology or skills from hiding a failed legal, quality or confidentiality safeguard. |
| Evidence confidence and unknown status | Separates absence from lack of evidence and makes weak claims visible. |
| Fitness for use and statistical quality | Tests relevance, accuracy, reliability, timeliness, coherence, comparability, accessibility and interpretability. |
| Professional statistical authority | Keeps methods, estimates, revisions and releases under accountable statistical control. |
| Controlled pilot discipline | Requires a benchmark, locked test, subgroup analysis, reproducibility, monitoring and fallback. |
| Resource proportionality | Allows different institutional arrangements while preserving minimum safeguards. |
| Action and sustainability focus | Connects recommendations to ownership, financing, recurring costs, procurement, monitoring and exit. |

# 4 Coverage assessment

| Required area | Coverage | Comment |
| --- | --- | --- |
| Economic social agricultural environmental and habitat domains | Complete by adaptable architecture | Domain examples vary, but the method is not tied to one sector. |
| Surveys censuses and administrative records | Complete | Data acquisition and process implications are addressed. |
| Research and technological information | Complete | Research institutions and experimental assets are explicitly mapped and gated for generalization. |
| Data collection and production processes | Complete | Workflow and GSBPM-aligned stages are represented. |
| Data quality and fitness for use | Strong | Quality is treated as a decision condition rather than a final inspection. |
| Institutional and decentralized systems | Strong | The NSO coordination role and sector ownership can coexist. |
| Advanced and resource-constrained countries | Adequate with support | Minimum viable pathway should be made explicit in delivery materials. |
| Private data and alternative sources | Complete at framework level | Country applications will require jurisdiction-specific contracts and authority. |
| Generative AI and traditional machine learning | Complete | The package distinguishes use types and their failure modes. |

# 5 Consistency findings and required refinements

| Issue | Why it matters | Required Version 1.1 treatment |
| --- | --- | --- |
| Dimension crosswalk | 1A uses twelve dimensions while later summaries group them. Users may think concepts disappeared. | Publish a canonical crosswalk from twelve detailed dimensions to seven or eight executive themes. |
| Gate catalogue | Gate names vary slightly across 1A, 1C, 1E and 1F. The logic is consistent but transfer is manual. | Define one master gate catalogue with IDs, applicability and stage-specific evidence. |
| Risk and consequence terminology | Risk classes A–D, average risk scores and Low to Very high consequence levels serve different purposes. | Publish a mapping and state that inherent risk, consequence and residual risk are not interchangeable. |
| Action-plan ownership | 1C, 1D and 1E contain action fields while 1G is the national plan. Duplication can produce conflicting records. | Define 1G as the system of record; feeder tools retain source actions and stable IDs. |
| Identifier model | 1D uses stable IDs and 1E references them, but no package-wide naming standard exists. | Create one ID convention for institutions, assets, flows, needs, risks, use cases, pilots, decisions and actions. |
| Evidence references | Evidence is required throughout, but citation fields and confidence labels are not fully standardized. | Adopt a shared evidence-register schema and confidence vocabulary. |
| Version and change control | Each instrument has a version, but package-level compatibility is not specified. | Add a package manifest and compatibility table. |
| Field facilitation | The tools are operational but do not yet form a facilitator handbook. | Create country-session agendas, respondent routing, evidence-request lists and consolidation instructions. |

# 6 Duplication and system of record

| Information object | Create or maintain in | Referenced by |
| --- | --- | --- |
| Institution, data asset, flow, user need and coordination arrangement | 1D ecosystem map | 1B, 1E and 1G |
| Readiness response and evidence | 1B questionnaire | 1C and 1G |
| Maturity score, target and gate decision | 1C scoring workbook | 1E and 1G |
| Use case and portfolio decision | 1E toolkit | 1F and 1G |
| Pilot evidence and assurance decision | 1F protocol | 1G and production governance |
| National action, cost, indicator and annual status | 1G action plan | Programme management and Phase 2 |

Feeder instruments should not be stripped of their action fields because actions arise during diagnosis. The improvement is to assign stable action IDs and require approved national actions to be consolidated in 1G. Source records remain linked evidence, not competing plans.

# 7 Minimum viable and full implementation pathways

| Pathway | Suitable context | Minimum sequence |
| --- | --- | --- |
| Minimum viable assessment | Limited staff or financing, early national discussion, or one priority sector. | 1A scope; selected 1B respondents; 1D critical actors and flows; 1C gates and priority dimensions; up to three 1E use cases; one 1F pilot charter; concise 1G plan. |
| Standard national assessment | Country-wide diagnosis with several producers and data sources. | Complete 1A–1G workflow with stakeholder validation and costed three-year plan. |
| Advanced or federated assessment | Large decentralized system or established AI portfolio. | Sector assessments, shared standards, automated inventories, independent validation and national synthesis. |

## Minimum safeguards that never reduce

Named accountable statistical owner.

Lawful purpose and approved data access.

Statistical benchmark and acceptance criteria.

Secure approved environment.

Meaningful human review and release authority.

Reproducibility, monitoring, incident response and fallback.

# 8 Field test before broad rollout

The first application should be treated as a structured field test of the package as well as a country diagnostic. It should involve an NSO, at least two sector producers, an administrative-data owner and one research or geospatial institution. Agriculture is a suitable first domain because it exercises survey, census, administrative, research and earth-observation sources together.

| Field-test step | Output |
| --- | --- |
| Preparation | National sponsor, scope, institutional sample, document request and facilitator team. |
| Evidence collection | Completed 1B responses and selected interviews with cited evidence. |
| Ecosystem mapping | Validated actors, critical assets, flows, user needs and coordination gaps. |
| Consensus and challenge | Agreed readiness profiles, disputed findings and independent reviewer comments. |
| Use-case workshop | Prioritized portfolio with gate results and no more than three pilot candidates. |
| Pilot design | At least one complete Phase 1F charter and evaluation matrix. |
| National synthesis | Draft 1G diagnosis, action plan, costs, indicators and approvals. |
| Package evaluation | User burden, ambiguous questions, duplicated entry, missing fields, calculation issues and facilitator lessons. |

## Field-test success criteria

Institutions can complete the instruments without inventing evidence.

Material findings are traceable across tools through stable IDs.

Gate decisions are consistent when reviewed by different teams.

The resulting plan identifies realistic owners, dependencies and recurring costs.

At least one selected pilot can be expressed as testable claims and stopping rules.

Resource-constrained institutions can participate without being treated as uniformly unready.

# 9 Version 1.1 harmonization backlog

| Priority | Change | Timing |
| --- | --- | --- |
| 1 | Master data dictionary, identifier convention and evidence-register schema. | Before first field deployment. |
| 1 | Canonical gate catalogue and risk or consequence crosswalk. | Before first field deployment. |
| 1 | Handoff instructions and system-of-record rules. | Before first field deployment. |
| 2 | Facilitator handbook and minimum viable pathway. | During field-test preparation. |
| 2 | Localization guide for law, language, classifications and institutional arrangements. | During field-test preparation. |
| 2 | Accessibility and low-connectivity versions of data-collection materials. | During field-test preparation. |
| 3 | Formula-linked transfer or import between workbooks. | After workflow is validated manually. |
| 3 | Examples and completed case studies from agriculture and another domain. | After first field test. |

# 10 Phase 2 design principles

Phase 2 should not be a generic introduction to AI. It should train official statisticians and enabling staff to make competent decisions and produce the evidence required by Phase 1. The instruments therefore become the spine of the curriculum, laboratories and assessments.

| Principle | Application |
| --- | --- |
| Role based | Common core followed by pathways for statisticians, leaders, data stewards, IT and security, legal and procurement, and trainers. |
| Workplace anchored | Exercises use actual statistical products, controlled data and institutional procedures. |
| Evidence producing | Learners create registers, benchmarks, validation reports, decision logs and monitoring plans. |
| Progressive independence | Demonstration, guided practice, supervised application, independent capstone and workplace follow-up. |
| Assessment for competence | Completion requires observable performance, not attendance or recall alone. |
| Tool agnostic | Teach durable concepts and verification methods while using current tools for practice. |
| Resource aware | Provide manual, open-source and managed-service options with explicit trade-offs. |
| Train the system | Combine individual learning with governance, workflow redesign and managerial authorization. |

# 11 Proposed Phase 2 curriculum architecture

| Block | Purpose | Indicative learning products |
| --- | --- | --- |
| A Official statistics and AI foundations | Establish concepts, limits, statistical purpose and professional obligations. | Use-case statement and risk classification. |
| B Productive daily practice | Use assistants for reading, drafting, coding, metadata, analysis and quality support with verification. | Verified work log and reusable prompt or procedure. |
| C Data quality and fitness for use | Connect source quality, total survey error, administrative data and alternative sources to AI. | Data-quality and fitness assessment. |
| D Governance confidentiality ethics and security | Apply access, purpose, oversight, supplier and incident controls. | Data and tool clearance pack. |
| E Methods validation and statistical assurance | Design benchmarks, locked tests, subgroup analysis, uncertainty and reproducibility. | Evaluation matrix and validation report. |
| F Domain laboratories | Apply methods to surveys, censuses, administrative data, geospatial and research information. | Domain evidence pack. |
| G Institutional implementation | Design operating model, procurement, financing, change and monitoring. | Institutional action plan. |
| H Capstone controlled pilot | Complete the Phase 1F process for a real bounded use case. | Assurance case and scale, redesign or stop decision. |
| I Trainer and facilitator pathway | Deliver modules, coach projects and run the Phase 1 diagnostic. | Observed facilitation and adapted lesson plan. |

# 12 Audience pathways

| Audience | Required blocks | Depth emphasis |
| --- | --- | --- |
| All participants | A, B, C and D core | Professional judgement, verification and safe daily practice. |
| Official statisticians and methodologists | A–H | Quality, methods, uncertainty, reproducibility and domain application. |
| Senior leaders and managers | A, D and G plus capstone decisions | Governance, investment, risk acceptance and benefits realization. |
| Data stewards and source owners | A, C, D and selected F | Provenance, metadata, quality, access and change notification. |
| IT cybersecurity legal and procurement | A, D, E and G | Architecture, security, legal authority, contracts, continuity and audit. |
| Trainers and national champions | A–I | Content mastery, facilitation, assessment and localization. |

# 13 Assessment strategy

| Level | Assessment |
| --- | --- |
| Knowledge | Short diagnostic checks on concepts, risks, quality and statistical authority. |
| Guided skill | Structured exercises with known answers and explicit verification steps. |
| Applied skill | Incomplete or imperfect datasets requiring judgement, documentation and peer review. |
| Integrated competence | Team capstone using the Phase 1F protocol and institutional decision bodies. |
| Workplace transfer | Evidence after 30, 60 and 90 days that the method is used correctly in routine work. |
| Trainer competence | Observed delivery, feedback quality, adaptation and consistent scoring. |

# 14 Recommended delivery sequence

| Stage | Duration concept | Result |
| --- | --- | --- |
| Preparation and baseline | 2 to 4 weeks | Cohorts, role profiles, digital access, selected use cases and initial skills evidence. |
| Common core | 3 to 5 learning days distributed over time | Shared language, safe practice and verified daily productivity. |
| Role pathways | 4 to 10 learning days depending on role | Role-specific evidence products and supervised practice. |
| Domain laboratories | 2 to 6 weeks part time | Completed analyses using controlled statistical data. |
| Capstone pilot | 8 to 16 weeks workplace based | Phase 1F assurance case and decision. |
| Trainer development | Parallel and extended | Local faculty capable of delivery and coaching. |
| Post-course follow-up | At 30, 60 and 90 days | Adoption evidence, corrections and management decisions. |

# 15 Immediate next work products

| Order | Product | Purpose |
| --- | --- | --- |
| 1 | Phase 2 curriculum blueprint | Define competencies, modules, pathways, prerequisites, hours and assessments. |
| 2 | Module 1 detailed lesson package | Establish the production standard for objectives, instruction, exercises, datasets, facilitator notes and assessment. |
| 3 | Practical laboratory design standard | Specify controlled data, expected artefacts, verification, difficulty and scoring. |
| 4 | Competency and assessment framework | Define observable performance by role and level. |
| 5 | Facilitator and train-the-trainer framework | Enable consistent delivery and national adaptation. |
| 6 | Learning platform and content-publication plan | Decide how materials, exercises, updates and learner evidence will be managed. |

# Final recommendation

Phase 1 should be accepted as the programme’s Version 1 operational foundation. Begin Phase 2 with the curriculum blueprint, while treating the first country application as the formal field test that will generate Version 1.1 of the diagnostic package. The next deliverable should be the Phase 2 Curriculum Blueprint and Competency Architecture, not a website or a sequence of isolated lessons.